**Governance & Oversight Approach & Methodology**

The Governance and Oversight (GO) service provides for the implementation of a cross-functional group and policy to govern the BCP program, its implementation and ongoing management and administration.

The GO approach/process is *generally* comprised of the following five phases:

|  |  |
| --- | --- |
| **Phase I – Information Gathering & Preparation** |  |

**Project Components:**

* Meet with the Client Project Leader and others as needed to review the MHA GO process, roles and responsibilities, meeting agenda and minutes.
* Identify members for the GO group. It should be a cross-functional group of business and technology. Members may include:
	+ BCP Sponsor
	+ IT
	+ Human Resources
	+ Finance
	+ Risk Management
	+ Corporate Communications
	+ Business Operations
* Limit the number of members to 10 people or less. Ensure the team members have the authority to act and make decisions.
* Document the roles and responsibilities.
* Document the BCP policy.
* Review proposed team with the BCP Sponsor and secure approval.

|  |  |
| --- | --- |
| **Phase II –**  |  |

**Project Components:**

* Distribute roles/responsibilities and policy documents to the team members.
* Schedule initial meeting of the Governance and Oversight team.
* Create agenda for the initial meeting.

|  |  |
| --- | --- |
| **Phase III –**  |  |

**Project Components:**

* Hold initial meeting of the Governance and Oversight team.
* Schedule future meetings based on discussion/decisions in the meeting.
* Create meeting minutes and distribute to team members.

|  |  |
| --- | --- |
| **Phase IV –**  |  |

**Project Components:**

* Hold ongoing meetings.